SPRINT PLAN

Western Materials Quoting App MVP

3-Week Day-by-Day Execution Plan

Phase 1 MVP  •  Pre-Build  •  Build  •  Validate  •  Launch

John Montazeri  •  Western Materials

Document Version 1.0  •  May 2026

# Sprint Overview

This document is the day-by-day execution plan for the Western Materials Quoting App MVP. It assumes John drives the build using Claude Code (Claude Max plan) as primary builder, Codex (Pro plan) as code reviewer, and a junior dev assistant for parallel work on lower-risk modules. Plan Mode is mandatory for every multi-file change.

## Sprint Structure

- Pre-Build Day (Day 0): account setup, tool installation, repo creation, seed data load

- Week 1 (Days 1-5): foundation, schema, auth, customer module, vendor pricing

- Week 2 (Days 6-10): pricing engine, quote builder, approval workflow

- Week 3 (Days 11-15): integrations (Pipedrive sync, Google Maps, Quoter, Slack), testing

- Shadow Mode (Days 16-20): app runs in parallel with current process; team validates results

- Go-Live (Day 21): full cutover, current Excel/Quoter process retired for new quotes

## Daily Cadence

Each work day follows this rhythm:

- Morning (30 min): review yesterday's commit, run tests, plan today's work using Plan Mode in Claude Code

- Work block 1 (2-3 hours): focused building with Claude Code primary, Codex review at end of each major change

- Lunch + review (1 hour): walk away from screen, mentally process problems

- Work block 2 (2-3 hours): testing, integration, polish

- End of day (30 min): commit, push to GitHub, update build log, prep prompts for tomorrow

Use Plan Mode for Every Multi-File Change Claude Code's Plan Mode prevents 80 percent of the costly mistakes that happen when an AI confidently edits files it does not understand. Before any change that touches more than one file, type /plan in Claude Code, let it think, then approve or refine. This is non-negotiable.

## Roles During Build

- John (primary builder): drives Claude Code, makes architectural decisions, owns the build log

- Junior dev assistant (parallel work): handles isolated modules like seed data verification, UI polish, basic CRUD pages under John's direction

- Codex (reviewer): pasted code for review before commit; flags issues Claude Code missed

- Gloria, Kristina, Claudina, Carlos (testers): join from Day 16 (shadow mode) to validate against real workflow

- Judd (approval testing): joins from Day 13 to test approval flow as backup approver

# Day 0: Pre-Build Setup

Complete these tasks before Day 1. Skipping any of these will cause day-1 friction.

### Account and Tool Setup

- Supabase project created (name: "wm-quoting-app"); URL and anon key saved

- Vercel account verified; project not yet created

- GitHub repository created (private; name: "wm-quoting-app")

- Claude Code installed and authenticated with Claude Max account

- Codex (Pro) accessible from browser or terminal

- n8n instance running (self-hosted recommended; cloud trial acceptable for first week)

- Google Cloud Console: Maps Distance Matrix API enabled, key generated

- Pipedrive API token generated (Settings → Personal Preferences → API)

- Quoter API token (if API access available; check Day 12 backup plan if not)

- Slack workspace verified; channel #wm-quote-approvals created

### Code Foundation

- Repository initialized with Next.js 15 + TypeScript + Tailwind + shadcn/ui

- CLAUDE.md file added to repo root (from Prompt Pack)

- AGENTS.md file added to repo root (from Prompt Pack)

- Supabase client SDK installed and connected

- Environment variables set in .env.local and Vercel

### Data Foundation

- Seed Data SQL Pack reviewed (do not run yet; will run Day 2 after schema)

- Pipedrive customer export downloaded as CSV (for Day 4 import)

- Vendor pricing Google Sheet confirmed accessible (URL noted for Day 3 reference)

### Exit Criteria for Day 0

- Empty Next.js app deployed to Vercel and accessible at a temporary URL

- Supabase project responding to basic queries from the app

- All API tokens stored securely in .env.local (and Vercel for production)

- GitHub repo has initial commit; CLAUDE.md and AGENTS.md in place

- John has tested Claude Code is working with /plan mode enabled

# Week 1: Foundation

Schema, authentication, customer module, vendor pricing module.

Day 1: Database Schema and Authentication

Tasks:

- Run Seed Data SQL Pack Part 1 (organizations, users, roles, feature_flags tables)

- Implement Supabase Auth with magic-link email authentication

- Add allowlist: only the 6 user emails (john, admin, estimate, bid, dispatch, info @westernmaterials.net) can sign in

- Build login page with magic-link send

- Build basic /dashboard page that displays the logged-in user's name and role

- Add row-level security (RLS) policies on all tables: organization_id check on every read/write

Exit criteria:

- All 6 users can log in via magic link

- Each user sees their correct role on the dashboard

- Attempting to query data from another organization fails (RLS test)

Day 2: Core Data Schema

Tasks:

- Run Seed Data SQL Pack Part 2 (plants, materials, truck_types, pricing_config, fees)

- Verify all 28 plants and ~400+ materials are loaded

- Build admin-only /admin page that lists plants and materials (read-only for now)

- Add audit_log table; create logAction() helper that every controller will use

- Wire up logAction() to capture user_id, organization_id, action, target_table, target_id, before_value, after_value, timestamp

Exit criteria:

- John can see all 28 plants in /admin/plants

- John can see materials grouped by plant

- Every page navigation creates an audit_log entry (proof of concept)

Day 3: Vendor Pricing Module (Read + Edit)

Tasks:

- Build /admin/plants/[plant_id] page showing all materials at that plant with current prices

- Add inline edit on price field for users with Admin or Account Manager role

- Add last_updated_at and updated_by_user_id columns to materials table; auto-populate on edit

- Build CSV bulk-upload UI: upload a CSV of plant_id, material_name, price; preview changes; commit

- Show price change history per material (last 10 changes)

Exit criteria:

- Gloria can edit a price inline and see the change reflected immediately

- John can upload a CSV with 50 price changes and see them applied

- Audit log shows who changed what price when

Day 4: Customer Module and Pipedrive Import

Tasks:

- Create customers table in Supabase with fields matching Pipedrive plus WM-specific fields (default_pit_id, pricing_notes, payment_terms, credit_status)

- Build one-time Pipedrive bulk import script: read CSV export, normalize, upsert to Supabase customers table

- Build /customers page listing all customers with search by name or company

- Build /customers/[id] page showing customer detail, last 5 quotes, default delivery address

- Add create-customer flow: estimator enters name/company/phone/email/address, saves to Supabase, queues Pipedrive sync (n8n picks up next cycle)

Exit criteria:

- All existing Pipedrive customers visible in WM app

- Search works in under 200ms for any customer name

- Estimator can create new customer in under 30 seconds

Day 5: Feature Toggle System and Admin UI

Tasks:

- Build /admin/feature-toggles page listing all toggles with on/off switches

- Implement check_feature(feature_name) helper that every gated feature uses

- Set Day 1 default toggles per PRD (Pricing Engine on, Approval Workflow on, Quoter Integration on, etc.)

- Build /admin/users page (Admin only): list users, change role, deactivate user

- End of week 1 review: run a full test of login + customer search + price edit + audit log

- Codex review of all code committed in week 1

Exit criteria:

- John can flip a feature toggle and see it take effect on next page load

- John can change Carlos's role from Estimator to Viewer and Carlos loses quote-create access

- All week-1 code passes Codex review without critical issues

# Week 2: Pricing Engine and Quote Builder

The core differentiating logic of the entire app. Spend time here. Test heavily.

Day 6: Pricing Engine: Core Calculation Logic

Tasks:

- Build pricing_calculator module with four-tier framework as input data (tier ranges from pricing_config table)

- Implement getMaterialPrice(material_id, customer_id, tier_override) function

- Implement getTruckingCost(distance_miles, truck_type, hourly_rate, deadhead_miles) function

- Implement applyMinimums(material_total, trucking_total, config) function

- Add Google Maps Distance Matrix integration: getDistance(origin_address, destination_address)

- Cache distance results in distances table to avoid repeated API calls

Exit criteria:

- Calling pricing_calculator with sample inputs returns correct totals for at least 5 test cases John defines

- Google Maps distance API working with caching

- All edge cases (zero quantity, missing plant, no available truck type) handled with clear errors

Day 7: Three-Zone Plant Selection

Tasks:

- Implement selectOptimalPlant(material_id, delivery_address, quantity) function

- Single-load logic: minimize total round-trip cost including deadhead from nearer yard (Acton or Sun Valley)

- Small-quote logic (2-3 loads): weighted optimization between material cost and trucking

- Large-quote logic (4+ loads): prioritize cheapest material

- Build plant comparison UI: show top 3 plant options with breakdown of why one wins

- Allow estimator to override plant selection with audit log capture

Exit criteria:

- For a test order (10 tons of 3/4 rock to Burbank), the system selects the lowest total-cost plant

- Estimator can override and the audit log records the override

- For a 100-ton order, the system prioritizes cheap material over short distance

Day 8: Quote Builder UI

Tasks:

- Build /quotes/new page: customer search, then quote line items (material, quantity, delivery address)

- Add line item editor: add/remove materials, see suggested plant per material, see suggested truck type

- Live pricing display: total material cost, total trucking cost, fees (fuel surcharge $79.95/load, environmental fee $29.95/load), tax, grand total

- Margin indicator: percentage margin shown in green (good) yellow (acceptable) red (low)

- Save as draft button (does not yet submit for approval)

Exit criteria:

- Gloria can build a 1-material quote in under 3 minutes

- Gloria can build a 3-material quote in under 6 minutes

- Margin indicator updates live as Gloria changes quantity

Day 9: Approval Workflow and Slack Notification

Tasks:

- Add quote status field: Draft, Pending Approval, Approved, Rejected, Sent, Viewed, Accepted

- Build submit-for-approval button on quote builder

- Build /approvals page (Admin only): queue of pending quotes with full detail and approve/reject buttons

- Implement approval action: records approver, timestamp, audit log entry, marks quote as Approved

- Wire up n8n workflow: Supabase webhook on quote submit → post to Slack #wm-quote-approvals channel with summary

- Slack message includes: customer, total, margin, who created it, link to view in WM app

Exit criteria:

- Gloria submits a quote and John sees it in /approvals within 5 seconds

- John sees the Slack notification in #wm-quote-approvals

- John approves and the audit log shows the approval timestamp

- Judd (logged in separately) can also see the same pending quote and approve it

Day 10: Quote Detail, Edit, and Versioning

Tasks:

- Build /quotes/[id] page showing full quote detail (read-only after approval)

- Implement edit-quote flow: anyone can edit a quote in Draft or Pending Approval status

- Lock editing on Approved quotes (only Admin can edit; create new version)

- Lock all editing on Sent quotes (must create a revision)

- Add quote history view: show all edits with who/when/what changed

- End of week 2 review: full quote lifecycle test (create → submit → approve → ready for Quoter push)

Exit criteria:

- Kristina can open Gloria's draft quote and edit it; audit log shows the edit

- Once John approves, Kristina can no longer edit (only Admins can)

- Quote history shows the full edit trail

# Week 3: Integrations and Testing

Day 11: n8n Workflows: Pipedrive Sync

Tasks:

- Build n8n workflow 1: Pipedrive customer sync (runs every 30 min, fetches recently-modified customers, upserts to Supabase)

- Build n8n workflow 2: New customer push (Supabase webhook → Pipedrive create)

- Build n8n workflow 4: Daily backup (Supabase export → Google Drive folder)

- Build n8n workflow 6: Weekly summary email (Sunday night → John's email with week stats)

- Test all workflows end-to-end with sample data

Exit criteria:

- Pipedrive customer edit reflected in WM app within 30 minutes

- New customer created in WM app appears in Pipedrive within 5 minutes

- Daily backup file appears in Google Drive folder

Day 12: Quoter Integration (or Fallback)

Tasks:

- Check Quoter API availability: confirm John has API access on his plan

- If yes: build n8n workflow 5 - on quote approval webhook, push draft to Quoter via API with line items, customer, prices

- If no: build PDF generation in WM app directly (using a PDF library) and email to estimator for manual handling

- Either way: store quoter_url or generated_pdf_url on the quote record

- Notify estimator via Slack DM when their approved quote is ready in Quoter (or as PDF)

Exit criteria:

- Approved quote appears as draft in Quoter (or as PDF in estimator's inbox)

- Estimator clicks the link in Slack DM and sees the quote ready to send

- Quoter URL stored in WM database for future reference

Day 13: Approval Flow Full Test

Tasks:

- Judd onboarded: tests approving quotes as backup admin

- Test self-approval flow: John creates a quote and approves it himself; audit log flags it

- Test request-changes flow: John clicks Request Changes on a quote; estimator notified; can edit and resubmit

- Test high-volume scenario: 10 quotes submitted in 30 minutes; both John and Judd review

- Test approval queue sorting: oldest first, with margin flags highlighted

Exit criteria:

- Judd successfully approves 3 test quotes

- Self-approval audit flag visible in the audit log

- 10-quote stress test completes without errors

Day 14: Polish and Bug Fixes

Tasks:

- Review all UI for consistency: spacing, typography, button placement, color usage

- Test on mobile (estimators in field will use phones occasionally)

- Fix any bugs found in week 2 testing that were deferred

- Add helpful empty states (no quotes yet, no customers yet, etc.)

- Add error messages that are clear and actionable (not stack traces)

- Codex review of all week 2 and week 3 code

Exit criteria:

- App looks consistent across all pages

- App works on mobile (read-only acceptable; create flows can stay desktop)

- Codex review surfaces no critical issues

Day 15: Performance and Security Pass

Tasks:

- Run pricing calculator with 50 quotes in sequence; verify no degradation

- Test customer search at 200+ customers; verify under 200ms

- Test RLS policies: log in as Gloria, attempt to read another org's data (should fail)

- Test feature toggle: turn off Approval Workflow, verify quotes go directly to Approved status

- Backup test: restore from a backup file and verify data integrity

- End of week 3: smoke test of entire system before shadow mode

Exit criteria:

- Performance acceptable across all major flows

- No security holes in RLS testing

- Feature toggle changes take effect correctly

# Shadow Mode (Days 16-20)

The app is feature-complete. Now the team validates it against real workflow without committing to a full cutover yet.

## Shadow Mode Protocol

- Every incoming customer quote request gets produced TWO ways: the old way (Excel + Quoter) and through the WM app

- The Excel/Quoter version goes to the customer (this is still production)

- The WM app version is for comparison only

- At end of each day, John reviews the WM app quotes vs Excel quotes for that day

- Discrepancies logged: what the app calculated, what Excel calculated, why they differ

- If app is consistently within 1-2 percent of Excel and discrepancies are explainable: ready for go-live

## Daily Shadow Mode Checks

- Day 16-17: just observe, do not change pricing logic; capture all discrepancies

- Day 18: fix any pricing logic discrepancies; ensure all 6 users have logged in and produced at least one quote each

- Day 19: stress test - produce 20+ quotes through the app in one day; verify no issues

- Day 20: go/no-go meeting with John and Judd; decision to go live Day 21 or extend shadow mode

Shadow Mode is Your Safety Net Resist the urge to skip shadow mode to launch faster. Every pricing discrepancy caught in shadow mode is a customer relationship saved at go-live. Five days of disciplined dual-tracking is the cheapest insurance you will ever buy.

# Go-Live (Day 21)

## Pre-Launch Checklist

- All 6 users logged in successfully in last 7 days

- Shadow mode showed no critical discrepancies for 3+ consecutive days

- All Phase 1 PRD acceptance criteria met

- Backup created and tested for restore

- Rollback plan documented (return to Excel + Quoter if app fails)

- John has committed 4 hours to be available for issues on Day 21

## Launch Day

- Morning: team meeting (30 min) - this is the cutover, all new quotes go through the app

- First quote of the day - John watches over Gloria's shoulder to confirm flow works

- Throughout day - John available on Slack for any issues

- End of day - retrospective with whole team: what worked, what was friction, what to fix tomorrow

## Post-Launch (Days 22-30)

- Daily 15-minute team check-in on app usage

- John fixes priority issues each evening using Claude Code

- Track success metrics: avg quote time, margin consistency, approval throughput

- End of Day 30: 30-day retrospective; decision to start Phase 2A

# Risk Register

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Quoter API not available | High | Use PDF-generation fallback; accelerate Phase 2A start |
| Pipedrive sync conflicts | Medium | Pipedrive is source of truth; WM app does not modify Pipedrive fields except for new customer creation |
| Pricing edge case missed | Medium | Shadow mode catches; manual override available for any quote |
| Estimator resistance to new tool | Medium | Pre-launch training; emphasize speed gain not control loss |
| John unavailable for approvals | Low | Judd as backup approver from Day 13 onward |
| Supabase RLS misconfiguration | Low | Multi-tenant testing on Day 1 and Day 15 |
| Build slips past 3 weeks | Medium | Cut from scope: AI features, advanced reporting, mobile optimization. Keep core pricing engine and quote builder. |
| Junior dev assistant introduces bugs | Medium | Pattern 1 review on every junior dev commit; junior dev handles only isolated modules |

# Scope Discipline

If the build runs hot, cut from this list before extending timeline:

## Cut First (Lowest Impact)

- Mobile optimization (desktop-only acceptable for v1)

- Advanced reporting and dashboards (basic counts acceptable)

- Bulk CSV upload for vendor prices (inline edit acceptable)

- Quote PDF custom branding polish (default template acceptable)

## Cut Second (Medium Impact)

- Three-zone plant selection (manual plant selection acceptable; just pick the right one)

- Multi-pit comparison UI (single plant per material acceptable)

- Audit log UI (database-only audit log acceptable; UI in Phase 2)

- Feature toggle UI (hardcoded defaults acceptable; UI in Phase 2)

## Never Cut (Core MVP)

- Four-tier pricing framework

- Trucking cost calculation

- Approval workflow

- Customer search and quote builder

- Quoter integration (or PDF fallback)

- Audit log database table (UI is optional)

- Multi-tenant database schema

End of Sprint Plan v1.0